## Slide 1
Social Interactivity Mentor for Youth with Autism
using the NAO Robot (SIMYAN)
Andrew Nguyen | Bryce George | Colton Homuth | William Ross
Sponsor - Dr. Adham Atyabi
Faculty Advisor - Mr. Bill Michael
November 20, 2020
Social Robotics 2
Weekly Report for 16-20 Nov 2020

## Slide 2: Week Summary:
Bryce had first session with the robot on 11/14
Full team writeups for first interactions complete
Tutorials for installing the NAO Python SDK and other utilities on Linux and Mac available in the repository wiki
High level requirements defined
Requirement specifications begun
Final Report begun with rough draft to be completed by 11/22

## Slide 3: Coming Week:
Member Meeting 11/20
  Complete requirement specifications
Members working on assigned sections of the Final Report
Member Meeting 11/22
  Compile rough draft of the Final Report
Create plan for setting up remote access to the robot
Final Presentation slides to be completed by 11/29